## RACI
RACI: R => Responsible A => Accountable C => Consulted I => Informed | Project Manager | Business Project Lead | Business Analyst | Developer | QA | Architects | Platform & Network Engineers | Application Integration Mgmt. Services | Security | Compliance | Production Management | Service Operations | Finance | Strategic Vendor Management
Initiation
Identify business stakeholders and agree on scope, benefits, high level requirements | x | x | x |  |  | x |  |  | x | x
Initial hardware/software Non-Functional Requirements (NFR) assessment | x | x |  | x | x | x | x | x | x | x |  |  |  | x
Complete Project Initiation Proposal (PIP) | x | x | x |  |  | x |  |  | x | x |  |  | x
Planning & Analysis
Planning
Define Implementation Approach & Strategy | x | x | x | x | x | x |  |  | x | x | x | x
Legal Documents | x | x | [11 empty] | x
Project Management Plan | x |  | x | x | x | x |  |  | x | x | x | x
Security and Compliance Plan | x |  | x | x |  | x |  |  | x | x
Integrated Project Plan | x | x | x | x | x | x | x | x | x | x | x | x
Determine Named Resources | x | x | x | x | x |  | x | x | x | x | x | x
Define Training Requirements - Business | x | x | x |  | x |  |  |  | x | x |  | x
Requirements
Business Requirements Documentation (BRD) | x | x | x | x | x |  |  | x | x | x
Business Work/Process Flows - Current and Future State | x | x | x | x | x |  |  | x | x | x
Non-Functional Requirements (NFR):
Compliance Requirements | x | x | x | x |  |  |  |  | x | x
Reliability, Availability, Service Levels, etc. | x | x | x | x |  | x | x | x |  |  | x
Validate Sizing (capacity) | x |  | x | x |  | x | x | x | x
Implementation Standards, Constraints | x |  |  | x | x | x | x | x | x
Training Requirements - Business & Support |  | x | x |  |  | x |  |  |  |  | x | x
Initial Risk Assessment | x |  | x |  |  | x |  |  | x | x |  | x
High Level Solution Architecture & Review | x |  | x |  |  | x |  |  |  | x |  | x
Security & Compliance Review | x |  | x | [5 empty] | x | x
Information Flow - Data | x | x | x |  |  | x |  | x | x | x
Development
Design
Update Non-Functional Requirements | x | x | x |  |  | x | x | x |  |  | x | x
Functional Design | x |  | x | x | x | x |  | x | x | x |  | x
Solution Design | x |  | x | x |  | x | x | x | x | x |  | x
Define Test Strategy | x | x | x |  | x | x | [5 empty] | x
Disaster Recovery Requirements | x | x | x | x |  | x | x | x |  | x | x | x
Create Detailed Test Plan | x | x | x | x | x |  | x | x | x | x
Technical Signoff | x |  | x | x |  | x | x | x | x | x | x | x
Build
Finalized Development Methodology | x |  |  | x |  | x |  | x
Development | x |  |  | x |  | x | x | x | x |  |  |  |  | x
Test and Production |  |  |  | x | x |  | x | x | [5 empty] | x
Build-out Development Environments | x |  |  | x |  |  | x | x |  |  | x | x
Build and/or Integrate Solution | x |  |  | x |  | x | x | x
Create Service Operations Turnover (TSO) | x |  |  | x |  |  | x | x | x | x | x | x
Conversion Activities and Execution | x |  | x | x |  |  |  | x
Test
Conduct Tests per Testing Strategy | x |  | x | x | x |  | x | x | x | x
QA Team Executes Tests | x |  | x | x | x |  | x | x
QA Team Logs Defects | x |  | x | x | x
User Acceptance Tests | x | x | x | x | x
Execute Training Plan | x | x | x |  |  | x |  |  |  | x | x | x
Conduct Training - Support | x | [5 empty] | x | x | x | x | x | x
Conduct Training - Business | x | x | x | [8 empty] | x
Deploy
Document Service Operations Turnover | x | x | x | x |  |  | x | x | x | x | x | x
Execute Deployment Check List | x |  | x | x |  |  | x | x | x |  | x | x
Closing
Post-Implementation Support |  | x |  |  |  |  | x | x | x | x | x | x
Collect & Archive Project Documentation | x | x | x | x | x | x | x | x | x | x | x | x

## Team Roster
Team Roster: | Phone | EMail | Department | Office Phone | Cell Phone | Functional Manager | Backup POC | PTO
Project Manager
Business Project Lead
Stakeholders
User Acceptance Testing (UAT)
Business Analyst
Developer
QA
Architects
Platform & Network Engineers
Application Integration Mgmt. Services
Security
Compliance
Production Management
Service Operations
Finance
Strategic Vendor Management

## Communications Plan
Target Audience | Comms Message / Activity | Comms Channel | Responsibility | Date of Message Delivery | Notes
Who needs to be told? | What message needs to be delivered to this audience? | How will you deliver the messsage? | Who will deliver the message? | When will the message be delivered? | Indicate budgetary needs; approvals; interdependencies